Using Metrics for Improvement

How will we know a change is an improvement? Proper measurement provides an objective gauge of the project success (or failure)

WHY

- Evidence-based - Metrics (or measures) focus on objective evidence rather than feelings or opinions.

  - To quantify the magnitude of the problem

  - To assure that a change is actually an improvement - tracking progress over time.

- Outcome-oriented - Metrics focus on the outcome articulated in the project aim statement. As the saying goes, “What gets measured, gets fixed.”

- Visual - Metrics, when presented graphically, tell a powerful story. Visible data, displayed and tracked over time, is key to attracting and sustaining the engagement of the team and stakeholders in the improvement work.

WHEN

Throughout the DMAIC process

- Define/Measure - to understand the magnitude of the problem

- Analyze - to assist in assessing the root cause

- Improve - to test & select the solution

- Control - to insure sustainability by monitoring the metric over time

HOW TO

| METRIC SELECTION |  |  |
| --- | --- | --- |
| 1. | Select the most appropriate metrics - Refer to the fundamental questions in The Model for Improvement - Brainstorm with the team to get the best ideas - See Metric Primer below |  |
| 2. | Clearly define the specifics for each selected metric. For example: - If measuring errors (or the lack thereof), specify the meaning of “error free.” - If measuring whether or not the requirements are met, clarify if all of the requirements have to be met, or only a percentage of the requirements? |  |
| METRIC PRIMER. Types of measures; What can you measure?. Improvement relies on measuring the following aspects of the process: - Inputs – What is needed to execute the process & deliver the outputs? - Process – Steps within the process - Outcome – Big picture, high-level goals; What does this process do or produce? - Balancing or Counterbalance – Side effects or unintended consequences in upstream or downstream steps or processes; Consider the following (not an exhaustive list): - Time – hours, minutes, days, months, length of stay, turn-around time, wait time, etc. - Errors or defects - Number of events, people, etc. - Satisfaction - Efficiency - Productivity - Cost - Value - Throughput / Flow - Access. What makes an ideal metric?; Key components of a metric. The best metrics have the following characteristics: - Direct linkage to the desired outcome or process (or a closely linked proxy) - Powerful enough to demonstrate the effects of the change - Meaningful to the project and stakeholders - Realistic to collect; A metric must have: - A numerator – The proportion of the study population that met the set requirements. Example: # of patients with viral load testing ordered - A denominator – The entire study population, or all subjects reviewed in a selected sample. Example: # of patients eligible for viral load testing according to country algorithm. |
| DATA COLLECTION |  |  |
| 1. | Create a data collection log (see Data Collection Log Example) Make sure you include all data needed to calculate the metrics. Consider the following: - The numerator (data to assure that the subjects meet the requirements of the study) and the denominator (data to assure all the eligible population is accounted for): - If evidence is required for an eligibility determination, consider a descriptive subheading or including an additional column in the log to verify the presence of that evidence - If the eligibility determination requires several steps, consider including a column in the log for each step required - Any demographic data deemed important, such as sex, age, pregnancy status - Any medical record or national identification numbers needed to trace back to the patients in the future - Any site identification or site-specific data (e.g., a specific specialty clinic within the site) |  |
| 2. | Collect Baseline Data Using the data collection log, at the initiation of the project, collect baseline data to understand the magnitude of the issue - Collected before any changes are made in the current process - Data Source – Specify source of data - Depending on the process, data may be collected retrospectively (i.e., chart review) or prospectively - Potentially may be abstracted from data already being collected - At least 25 data points are needed |  |
|  | Tips: - Include definitions on the log so staff who may not be members of the team will be able to easily interpret and use the log - Use small tests of change - Create a paper-based log first. Test the log through multiple iterations before finalizing or transferring to an electronic format. - Make sure you have all the information needed to calculate the study metric. |
| 3. | Create a data collection plan (see the Data Collection Plan template) [Instructions for creating Plan included in the template in gray print] |  |
| DATA DISPLAY |  |  |
| 1. | Create a run chart to track the metrics over time |  |
|  | - A run chart is a graphical representation of change over time - It is one of the best ways to display Quality Improvement (QI) data |  |
|  | Steps to create a run chart: - Title the chart and label the axes - Place the selected metric on the vertical or y-axis - Place time on the horizontal or x-axis - Plot your metric over time - Include a goal line (frequently shown in red ink), indicating the team’s goal for the selected metric - Annotate the run chart, marking the tests of change along the timeline (See examples in PowerPoint presentation) - Keep the data up-to-date, posting weekly or as frequently as possible You may also use the Excel Run Chart Template to create run charts automatically |  |
| 2. | Display the data on the project learning board (See Project Management Tools – Learning Board) |  |
| 3. | Review and update the data regularly (daily, weekly or monthly) with the staff & the QI team (See Project Management Tools - Meeting Facilitation templates) - When reviewing the data, assess the trend and determine what additional “tests of change” need to be conducted to continue a desired trend or reverse an undesired trend. (See Model for Improvement – PDSA) - Obtain input from the front-line workers. What is working well? What is not working well? |  |

Templates:

- Quality Improvement Project Outline

- Data Collection Log Example

- Data Collection Plan

- Run Chart Template (Excel)

Resources:

IHI QI Essentials Toolkit:

Run Chart & Control Chart

Data Collection: Key Planning Questions

Microsoft Excel Workbook: Insert  Chart  Line Chart

Data Collection Log Example

High Viral Load (HVL) Patients with Follow-Up Appointment

Metric = # of appointments made within 48 hours of receiving HVL results / All HVL Results

| Patient ID | Age | SEX | VL Results (cp/ml) | Date of VL Testing | Date of VL Results at CTC | HVL (YES/NO) | Phone Call Made /Appointment Date | Follow-up Visit for EAC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Data Collection Plan

| Who | - Who is responsible for the collection, display and analysis of the data? - If a series of data needs to be collected by different cadres, map the process of data collection from beginning to end |
| --- | --- |
| How Often | - Specify data collection frequency - hourly, daily, weekly or monthly - Determine the collection cutoffs for the time frame selected. - Consider the project metric and what makes sense in the collection cycle. When must the data be submitted for each cycle? |
| What | - Specify what is included or excluded - Determine the data source and sample size - Draw the data collection log showing what data will be captured |
| Where | Specify a location – e.g., a clinic, unit or department |
| How | Given the log, will data be collected at time of seeing the patient or actual event (real-time) or collected retrospectively through chart or record review? |
| Training | Who will be responsible for training the staff about the data collection? Specify how, when and where. |
| Sustainability – See Control Plan | Early in the project, determine who will own the process and the metric at project completion. How will the metric be monitored when the project is complete? (See Control Plan) |

Data Display - Run Chart Template (Excel)