## Slide 1: Action Items Following LS #2
LARC Zimbabwe

## Slide 2: Action Items Following LS #2
Action Items | By When?
Update LS#1 Deliverables / PPT: Use template, Remove all orange font, Update Summary Slide; VOC - Evaluate Data – Include Data Table, Differentiate Baseline from Post-Intervention Data | 17 FEB
Conduct Team Meetings (Weekly) | WEEKLY
Submit Data to MOH | 7th of each month
Create Learning Board | 17 FEB
5S | 7 MAR
Visual Management | 7 MAR
PDSA #1 | 14 FEB
PDSA #2 and more | 28 FEB
Standard Work (SOP) for AIM #1 and #2 | 15 APR
Future State Map for AIM #1 and #2 | 15 APR
Data Display – Begin Run Chart for AIM #1 and #2 | 7 FEB for Aim #1 17 FEB for Aim #2
Presentation for LS #3 | 30 APR